# MyZubster LIFE 2026 – Consortium Brief

Proposed consortium architecture for LIFE Circular Economy and Zero Pollution

MyZubster | LIFE 2026 | Working Draft – 20 August 2026

Target call: LIFE-2026-SAP-ENV-ENVIRONMENT ¦ Deadline: 22 September 2026, 17:00 CEST

# 1. Project positioning

MyZubster LIFE is positioned as a demonstration and replication project combining digital environmental infrastructure, sensor integration, water-quality monitoring and independent MRV. The consortium should be built around four functions that are immediately legible to a LIFE evaluator: public authority, technology, independent validation and real operational pilot.

# 2. Recommended consortium core

- Public/institutional coordinator – project governance, policy integration, administrative capacity and replication.

- MyZubster – technology and data partner, leading the digital platform, API/data architecture, dashboards, sensor integration and analytics.

- ENEA – independent scientific validation and MRV lead, defining indicators, QA/QC, reference protocols and validation of sensor-derived data.

- Hera – operational pilot and water-utility partner, providing a real demonstration environment, operational data and industrial validation.

- ATER​SIR / Consorzio di Bonifica / equivalent governance or end-user partner – territorial replication, water governance and adoption pathway.

# 3. Why this architecture is credible

ENEA and Hera already have a concrete collaboration at the Cesena wastewater-treatment plant on real-time monitoring of treated wastewater for irrigation suitability. The system addresses microbiological and quality parameters in the context of Regulation (EU) 2020/741. This creates a strong technical bridge for a LIFE demonstration in which MyZubster can add the digital integration, data layer, traceability, decision support and replication architecture.

The Emilia-Romagna ecosystem is also active on wastewater reuse. In 2026, regional agreements formally involve Regione Emilia-Romagna, ATERSIR, Hera, reclamation consortia and ARPAE in reuse, monitoring and technical-governance activities. This materially strengthens the replication and policy narrative.

# 4. Proposed Work Package structure

| WP | Title | Lead | Core scope |
| --- | --- | --- | --- |
| WP1 | Project Management & Governance | Public coordinator | Governance, LIFE reporting, financial/admin management, risk and ethics. |
| WP2 | Digital Environmental Infrastructure | MyZubster | Platform, data architecture, APIs, dashboards, IoT/sensor integration, alerts and traceability. |
| WP3 | Monitoring, Sensors & MRV | ENEA + MyZubster | MRV methodology, QA/QC, data validation, environmental indicators and reference measurements. |
| WP4 | Demonstration & Validation | Hera + ENEA | Pilot installation, baseline, operational demonstration, performance verification and user feedback. |
| WP5 | Environmental & Socio-economic Impact | ENEA / university | Water/resource efficiency, pollution reduction, impact indicators, cost-benefit and sustainability assessment. |
| WP6 | Replication, Exploitation & Policy | Coordinator + governance partner | Replication package, policy uptake, exploitation strategy, business model and territorial transfer. |
| WP7 | Communication & LIFE Dissemination | Coordinator / ecosystem partner | Stakeholder engagement, dissemination, LIFE communication and capacity building. |

# 5. Consortium design principles

- Keep the core consortium compact: five to six beneficiaries are preferable to a large group with overlapping roles.

- MyZubster should lead WP2, not appear only as a technology supplier inside the pilot.

- ENEA should be framed as independent validation/MRV lead rather than a generic research partner.

- Hera should be framed as a demonstration and operational-validation partner, not simply a pilot host.

- Add a university only where it contributes a clearly distinct scientific capability not already covered by ENEA.

- Secure letters of commitment, operational pilot access and partner budget inputs as early as possible.

# 6. Immediate decisions

- Confirm the preferred public/institutional coordinator.

- Open parallel discussions with ENEA and Hera around a shared pilot concept.

- Select the territorial governance/end-user partner: ATERSIR, reclamation consortium or equivalent.

- Freeze the pilot site, target environmental problem and measurable baseline/target indicators.

- Convert the WP architecture into partner person-months, direct costs and deliverables.

## Sources

CINEA – LIFE Calls for proposals 2026: https://cinea.ec.europa.eu/life-calls-proposals-2026_en

CINEA – LIFE-2026-SAP-ENV-ENVIRONMENT: https://cinea.ec.europa.eu/funding-opportunities/calls-proposals/standard-action-projects-saps-circular-economy-and-zero-pollution-environment-0_en

ENEA – Ambiente: acque reflue, da ENEA e Hera nuove tecnologie per il riutilizzo (14 March 2024): https://www.media.enea.it/comunicati-e-news/archivio-anni/anno-2024/ambiente-acque-reflue-da-enea-e-hera-nuove-tecnologie-per-il-riutilizzo.html

Regione Emilia-Romagna, BURERT n. 98/2026 – accordo Regione, ATERSIR, Hera, Consorzio Bonifica Renana: https://bur.regione.emilia-romagna.it/dettaglio-inserzione?i=ce5857b3d73f4b6a9a2bdd5721dd34e8

Regione Emilia-Romagna, BURERT n. 125/2026 – rinnovo accordo riuso acque reflue: https://bur.regione.emilia-romagna.it/dettaglio-inserzione?i=96357f100455499295b27b6f38b1f813